## Status Report
Status Report for Team Bubbles - Class Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-07-20 | Overall Status: | Yellow
Contact: | Dwight | Explanation: | 2 of our 4 developers will be on PTO for the next 3 days.
Prepared By: | Assistant to the Team Lead
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Bob Smith | Wrote 20 of 25 unit tests |  | 80% complete
Jane Doe | Wrote 3 of 4 DAO's |  | 75% complete
List all team members here
ID # | Key Issues | Action Plan |  |  | Status
1 | Can't connect to deployed DB | connect to local DB as backup plan |  |  | Open
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | NA | 2020-07-20 | 100% complete
Back-end |  | poor | 2020-07-21 | 30% complete
Business logic |  | good | 2020-07-21 | 80% complete
Front-end |  | good | 2020-07-22 | 80% complete
Testing |  | average | 2020-07-22 | 40% complete
Presentation |  | excellent | 2020-07-23 | 90% complete
[make your own milestones]